## Sheet1
Objectives | Status | Prefered Order | Progress % | Dependencies | Completion Date
Create a barebone application | Complete | 1 | 100% |  | 2019-05-23
Port Cyril's Provisioning implementation | Complete | 2 | 100% |  | 2019-05-27
Create a Button Library Module | On Hold | 3 | 80% | 6 | 2019-05-29
Create a UART Module | In Progress | 4 |  |  | 2019-05-31
Development of Test Interface | In Progress | 5 |  |  | 2019-06-05
Create I2C Interface |  | 6 |  |  | 2019-06-06
Create Temp/Humidity Library Module |  | 7 |  |  | 2019-06-10
Create Touch Sensor Library Module |  | 8 |  |  | 2019-06-11
Create PWM Module |  | 9 |  |  | 2019-06-11
Create LED Strip Module |  | 10 |  |  | 2019-06-12
Create Proximity Sensor Library Module |  | 11 |  |  | 2019-06-12
Create a Status LED Library Module |  | 12 |  |  | 2019-06-13
Interface Provisioning with Button Module |  | 13 |  |  | 2019-06-17
Interface Provisioning with LED Library Module |  | 14 |  |  | 2019-06-17
Refactor SimpleLink Manager into Network and Application Manager |  | 15 |  |  | 2019-06-19
OTA programming functionality inclusion |  | 16 |  |  | 2019-06-21
Design AWS mqtt services |  | 17 |  |  | 2019-06-24
Create Accelorometer Library Module |  | 18 |  |  | 2019-06-25
Create NFC Reader Library Module |  | 18 |  |  | 2019-06-27
System exception state handling and recovery |  | 19 |  |  | 2019-07-01

## Sheet2
TF Development
| Objectives | Status | Progress % | Dependencies | Completion Date
TF Dev LED Strip, Sense Flex
| Part Identification | Complete | 100% |  | 2019-05-29
| BOM Generation | In progress | 50% |  | 2019-06-03
| Parts Procurement | In progress | 100% |  | 2019-06-04
| Fixture Design | Not Started | 50% |  | 2019-06-05
| Wiring |  | 50% |  | 2019-06-07
| Firmware Development | In progress | 30% |  | 2019-06-10
| Firmware Testing | Not Started | 0% |  | 2019-06-11
| Pre-DUT Testing | Not Started | 0% |  | 2019-06-11
| Final Build | Not Started | 0% |  | 2019-06-12
| Release to Production | TBD |  |  | TBD
| Objectives | Status | Progress % | Dependencies | Completion Date
TF Dev LID Board
| Part Identification | Not Started | 0% |  | 2019-06-14
| BOM Generation | Not Started | 0% |  | 2019-06-17
| Part Procurement | Not Started | 0% |  | 2019-06-18
| Fixture Design | Not Started | 0% |  | 2019-06-20
| Wiring | Not Started | 0% |  | 2019-06-21
| Firmware Development | Not Started | 0% |  | 2019-06-25
| Firmware Testing | Not Started | 0% |  | 2019-06-26
| Pre-DUT Testing | Not Started | 0% |  | 2019-06-26
| Final Build | Not Started | 0% |  | 2019-06-28
| Release to Production | TBD |  |  | TBD